## Prioritization
Item | Reach | Impact | Confidence | Effort | RICE Score | MVP | Rationale
Publish to YouVideo | 4 | 4 | 5 | 3 | 26.6667 | No | YouTube is a very popular influencer platform and many users may use this feature.
Publish to TikTak | 4 | 3 | 5 | 3 | 20 | No | YouTube is a very popular influencer platform and many users may use this feature.
Publish to Fastgram | 2 | 2 | 5 | 3 | 6.6667 | No | Fastgram is a less widely used tool. This may not be widely used
Create app to edit the clips and text | 5 | 5 | 3 | 5 | 15 | Yes | Users already spent considerable time edting clips and text. It's unclear how another app for this purpose would reduce frustration.
Translate into other languages | 4 | 4 | 4 | 4 | 16 | No | Language translation could be of benefit to our customers in other geographies.
Generate video title, video description, and recipe summary | 5 | 5 | 4 | 4 | 25 | No | This is a core part of the product value proposition. Users spend considerable time editing video, adding captions, and writing detailed recipes.
Build Extensions API | 3 | 3 | 3 | 5 | 5.4 | No | This could be a nice-to-have down the road. There may be third-party developers who could help broaden usage of our product through useful integrations.
Create Recipe Library | 3 | 3 | 3 | 4 | 6.75 | No | Our users likely have access to recipe libraries of their own and, in many cases, have their own recipes they want to share. This is a nice-to-have for the future roadmap.
Specify dataset | 5 | 5 | 5 | 2 | 62.5 | Yes | We can't produce an AI algorithm without data.
Publish to TastyTube | 5 | 4 | 5 | 2 | 50 | No | Publishing videos to TastyTube is an expected need.
Conduct exploratory user research | 5 | 4 | 5 | 2 | 50 | Yes | Exploratory user research is the first step in any product development initiative. We need to understand user pain points before we can develop effective solutions.
Select and instruct labeling team | 4 | 4 | 4 | 2 | 32 | Yes | We need a labeling team in place to annotate our initial data set as part of the MVP.
Conduct usability testing | 3 | 5 | 4 | 2 | 30 | Yes | Usability testing is a fundamental outcome of an MVP. We want to understand how our MVP is received by our test audience.
Generate video captions | 4 | 4 | 4 | 3 | 21.3333 | No | Users spend considerable time adding captions to videos.
Build ML model to classify recipe steps | 5 | 5 | 3 | 4 | 18.75 | Yes | This is a core part of the product value proposition. Users spend considerable time editing video, adding captions, and writing detailed recipes.
Build ML model to clip video into individual recipe steps | 4 | 4 | 3 | 4 | 12 | Yes | This is a core part of the product value proposition. Users spend considerable time editing video, adding captions, and writing detailed recipes.
Prepare data: Split videos into clips | 4 | 4 | 3 | 4 | 12 | Yes | This is a core part of the product value proposition. Users spend considerable time editing video, adding captions, and writing detailed recipes.
Prepare data: Apply labels | 4 | 4 | 3 | 4 | 12 | Yes | This is a core part of the product value proposition. Users spend considerable time editing video, adding captions, and writing detailed recipes.

## MVP Roadmap
Item | Sequence | # of Sprints | Resource | Dependencies
Specify dataset | 2 | 1 | Data Engineering team | Conduct exploratory user research
Create app to edit the clips and text | 8 | 1 | Engineering team | Build ML model to clip video into individual recipe steps
Conduct exploratory user research | 1 | 1 | Product team | Conduct exploratory user research
Select and instruct labeling team | 3 | 1 | AI Research team | Specify dataset
Conduct usability testing | 9 | 1 | Design team | Create app to edit the clips and text
Build ML model to classify recipe steps | 7 | 3 | ML/AI Engineering team | Build ML model to clip video into individual recipe steps
Build ML model to clip video into individual recipe steps | 6 | 3 | ML/AI Engineering team | Prepare data: Split videos into clips
Prepare data: Split videos into clips | 4 | 2 | Data Engineering team | Specify dataset
Prepare data: Apply labels | 5 | 5 | Data Engineering team | Select and instruct labeling team